## Sheet1
Financial Analysis for MindArt
Created by: Valletta Paolo Carmine, Zoccola Alessandro |  | Date: | 2024-10-14
Discount rate | 3.5%
Assume the project is completed in Year 0 |  |  | Year
| 0 | 1 | 2 | 3 | Total |  | Team | Ore Settimanali | Settimane lavorative | Stipendio Orario | numMembri | Totale |  | Team | Ore Settimanali | Settimane lavorative | Stipendio Orario | numMembri | Totale
Costs | 84678.125 | 5775 | 5775 | 5775 |  |  | Senior | 15 | 25 | 21 | 3 | 23625 |  | Senior | 3 | 25 | 21 | 1 | 1575
Discount factor | 1 | 0.97 | 0.93 | 0.9 |  |  | Junior | 15 | 25 | 16 | 7 | 42000 |  | Junior | 3 | 25 | 16 | 3 | 3600
Discounted costs | 84678.125 | 5601.75 | 5370.75 | 5197.5 | 100848.125 | [5 empty] | 10 | 65625 | [5 empty] | 4 | 5175
Benefits | 0 | 30312.5 | 41750 | 50050
Discount factor | 1 | 0.97 | 0.93 | 0.9 |  |  | Team | Attrezzatura | Hosting | Manutenzione | Team | Rischi | Totale |  | Team | Enti coinvolti | % risparmio operativo | Risparmio amministrativo | Incremento benessere psicologico | Benefici fondi pubblici | Totale
Discounted benefits | 0 | 29403.125 | 38827.5 | 45045 | 113275.625 |  | Anno 0 | 5000 | 600 |  | 65625 | 13453.125 | 84678.125 |  | Anno 0 | 10 | 0% | 0 | 0 | 0 | 0
[7 empty] | Anno 1 |  | 600 | 5175 |  |  | 5775 |  | Anno 1 | 15 | 15% | 2062.5 | 8250 | 20000 | 30312.5
Discounted benefits - costs | -84678.125 | 23801.375 | 33456.75 | 39847.5 | 12427.5 | NPV | Anno 2 |  | 600 | 5175 |  |  | 5775 |  | Anno 2 | 20 | 20% | 2750 | 11000 | 28000 | 41750
Cumulative benefits - costs | -84678.125 | -60876.75 | -27420 | 12427.5 |  |  | Anno 3 |  | 600 | 5175 |  |  | 5775 |  | Anno 3 | 25 | 24% | 3300 | 13750 | 33000 | 50050
ROI | 12.32%
Payback in Year 3
[15 empty] | Team | Percentuale | Totale
[15 empty] | Contingency Reserve | 10.5% | 6890.625
[15 empty] | Management Reserve | 10% | 6562.5
13453.125